## Person A
Day | Activities
Week 9
Monday | Discussion with group members. Person B suggested we should work with Dataset X because of Reason XYZ. Not finalized yet. Will continue tomorrow after we do more research.
Tuesday
Wednesday | Met up with Person B and Person C. Person D was absent and was uncontactable. We finalized the choice of our dataset. We have chosen Dataset Y. Will consult Prof ABC during tutorial.
Thursday
Friday | After discussion with Prof ABC, we finally know how to define an interesting question. Our DS project will be a regression problem.
Saturday
Sunday | Met up with all members on Sunday. Delegated tasks. I was tasked with data cleaning. The rest will look at other regression models.
Week 10
Monday | Having difficulties getting rid of NANs. Keeps giving me Index Error. Consulted ChatGPT to resolve this
Tuesday
Wednesday
Thursday | Finally managed to impute missing values. I realised that the dataset has a lot of outliers. Need to discuss this with the group
Friday
Saturday
Sunday | Met up with the group. Person B could not attend due Reason YYY. We went through some of the strategies proposed by Person C. Finalised on the strategy and formulation.
Week 11
Monday | Met up with Prof ABC. He suggested that we change our strategy as we are biting more than we can chew and we don't have much time. Called an emergency meeting with the group.
Tuesday | Finalised our strategy. Got the go-ahead from Prof ABC.
Wednesday | ML
Thursday | ML
Friday
Saturday | Prepare powerpoint slides
Sunday | Rehearsed presentation with group members. We are ready!